## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during development and include a detailed description of every step. Explain what problems you encountered, why you made certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log. If external sources where used as reference, please mention them in the description
Subject | Amount of hours | Date | Description | Bonus
DB, Bramus, Code | 1 | 2025-07-24 | Learn some knowledge about Bramus Routing, Get used to code, Test Db connection successfully
Sql Schema, Dump Data | 1 |  | Prepare tables structures for MySql and create some dummy data to test
FacilityController class creation |  |  | Create FacilityController class with initial functions when considering CRUD operations
Testing |  |  | Test GET (all or with facility ID get only one) operations for facility table
FacilityController Facility Update and Add | 1 | 2025-07-25 | Creating POST and PUT methods for facility (User can update and create facility)
Testing |  |  | Test POST and PUT methods and correct bugs/logic
Facility Controller Delete Facility | 2 |  | Create DELETE method for facility
Testing |  |  | Test DELETE method and correct bugs/logic
Facility Controller Search Function Added |  |  | Creating Search function for facilities with name, tag, location (not combined yet, search for only one criteria)
Testing |  |  | Test search function
Search function combination of criterias | 2 |  | Make search function more complex, it can be search by using name, tag and location at the same time
Testing |  |  | Test search function and correct logic
Partial search |  |  | Make search function usable for searching for location city ‘ams’ should return all facilities with city ‘Amsterdam’ and do it for all (name, tag, etc.)
Testing |  |  | Test partial search and correct logic
Adding Pagination | 1 |  | Add pagination for Listing all facilities and Search facilities functions | x
Testing |  |  | Test pagination and correct bugs | x
Adding sanitization |  |  | Sanitization for name, location,tags | x
TagController class creation | 2 | 2025-07-28 | Creating POST and PUT methods for tags (User can update and create a tag)
Testing |  |  | Test POST and PUT methods and correct bugs/logic
TagContoller Delete Tag |  |  | Create DELETE method for tag
Testing |  |  | Test DELETE method and correct bugs/logic
TagController List All Tags or A Tag |  |  | Creating List all tags (if wanted with cursor-based pagination) or a tag according to tag ID functions
Testing |  |  | Testing these functions and correct logic
EmployeeController Added | 1 |  | EmployeeController added with all CRUD operations | x
Testing |  |  | Testing all functions of EmployeeController and fix bugs | x
Repository classes added | 2 | 2025-07-29 | Split FacilityController class codes to repository logic
Testing |  |  | Test all methods and fix bugs (pagination correction)
Sanitizer and Validator classes | 1 |  | Sanitization and Validation classes added for more reusable code (basic regex, empty checking etc.) | x
Testing |  |  | Testing these two classes and fix bugs | x
Repository classes added | 1 |  | Split Employee and Tag Controller classes into their repositories and controllers to make single responsibility
Testing |  |  | Test these new classes and fix bugs
Location related classes | 1 |  | Location related repository completed and controller class added with CRUD operations
Testing |  |  | Test these new class/functions and fix bugs
Request Helper class added | 2 | 2025-07-30 | For more readable/reusable code Request Helper class added for reading data, cursor and limit
Testing |  |  | Test these and bug fixes
DTO Logic |  |  | DTO logic added for usability and reduce duplicate codes
Testing |  |  | Test and bug fixes
Add/Remove tag to/from facility | 1 |  | Adding and removing tag(s) from a facility logic is changed and some code cleaning is made.
Comment add | 1 |  | Proper comments (for example: usages) are added
Authentication | 1 |  | Basic Bearer token authentication is added, if not authorized then give unauthorized message | x
Testing |  |  | Testing authorization and bug fixes | x
PHPUnit Test case | 2 |  | For all repositories possible test cases are added and tested, bugs are fixed. Also some minor code changes are made for eliminate duplicate codes | x
Docker | 2 | 2025-08-01 | Running in docker container entegrated. (https://www.youtube.com/watch?v=qv-P_rPFw4c watched) | x
Others | 2 |  | Read.me, location and tag deletion correction, unit tests for these, hour log sheet, postman json, ER diagram, adding TOD0's etc
Total amount of hours | 19